## Consolidated Testing
Module | S/N | ID | Type of test | Sub-type of test | Description of test run (Click on the "+"on the left, to view parameters) | Correct outcome | Per expectations? (Y/N) | Comments | Bug history
Registration | 1 | Regi 1 | Validity of fields other than password | Attempt to use duplicate username | Fill in form using already existing username | Account should not be able to be created, and user should be asked to change to a non-duplicate username | N | To include validation against duplicate username | 2/6/2018 this bug was found 26/6/2018 bug remains
Registration and authentication | 1.1 | Regi 1.1 | Validity of fields other than password | Attempt to use duplicate username | Username: Jacky (same as existing Jacky) Mobile number: 81234567 Email: jackyy@hotmail.com Pw: jacky124 | Account should not be able to be created, and user should be asked to change to a non-duplicate username | N | To include validation against duplicate username | 2018-06-02
Registration | 2 | Regi 2 | Validity of fields other than password | Attempt to use invalid phone number | Fill in all 8 digits with numbers which are already existing in the database (duplicate mobile number) | Account should not be able to be created, and user should be asked to change to a non-duplicate phone number | Y | NIL as no bug | 2/6/2018 bug was found 26/6/2018 bug closed
Registration and authentication | 2.1 | Regi 2.1 | Validity of fields other than password | Attempt to use invalid phone number | Username: alexias Mobile number: 86543451 (same as existing Alexia) Email: alexiaa@hotmail.com Pw: alexia123 | Account should not be able to be created, and user should be asked to change to a non-duplicate phone number | Y
Registration | 3 | Regi 3 | Validity of fields other than password | Attempt to use invalid phone number | Do not fill in all 8 digits (eg. fill in 7 digits of phone number) | Account should not be able to be created, and user should be asked to fill in phone number correctly | Y for logic, N for UI | Currently for mobile number, it says "maximum of 8 digits", but it would be clearer to say "mobile number must have 8 digits only") | 2/6/2018 bug was found 26/6/2018 bug closed 26/6/2018 UI improvement pt found
Registration and authentication | 3.1 | Regi 3.1 | Validity of fields other than password | Attempt to use invalid phone number | Username: valeriee Mobile number: 9876543 (missing 1 digit) Email: valeriee@hotmail.com Pw: valeriee124 | Account should not be able to be created, and user should be asked to fill in phone number correctly | Y
Registration | 4 | Regi 4 | Validity of fields other than password | Attempt to use invalid phone number | Fill in some blanks with alphabets and special characters instead of numbers | Account should not be able to be created, and user should be asked to fill in phone number correctly | Y | NIL as no bug | 2/6/2018 bug was found 26/6/2018 bug closed
Registration and authentication | 4.1 | Regi 4.1 | Validity of fields other than password | Attempt to use invalid phone number | Username: timonthee Mobile number: t912345 (invalid phone number) Email: timonthee@hotmail.com Pw: timonthee123 | Account should not be able to be created, and user should be asked to fill in phone number correctly | Y
Registration | 5 | Regi 5 | Validity of fields other than password | Attempt to use duplicate email address | Fill in form using already existing email address | Account should not be able to be created, and user should be asked to change to a non-duplicate email address | N | Correctly denied creation of account, but the reason showed for the below test cases was "Number has already been used". The number was new. The reason should have been "Email address has already been used". | 26/6/2018 bug found
Registration and authentication | 5.1 | Regi 5.1 | Validity of fields other than password | Attempt to use duplicate email address | Username: alexsia Mobile number: 81111111 Email: alexia@hotmail.com (Same email as alexia) Pw: alexsia124 | Account should not be able to be created, and user should be asked to change to a non-duplicate email address | N |  | 2018-06-26
Registration and authentication | 5.2 | Regi 5.2 | Validity of fields other than password | Attempt to use duplicate email address | Username: valery Mobile number: 80000000 Email: valerie@hotmail.com (Same email as valerie) Pw: valery124 | Account should not be able to be created, and user should be asked to change to a non-duplicate email address | N |  | 2018-06-26
Registration | 6 | Regi 6 | Validity of fields other than password | Fill in all fields correctly | Fill in all fields correctly | Account should be created | N | As test case 1.1 shows, the ability to create new account is there, but there is a recurring bug of "phone number already used" (even though it's a new number) which prevents legitimate accounts from being created. | 26/6/2018 bug found
Registration and authentication | 6.1 | Regi 6.1 | Validity of fields other than password | Fill in all fields correctly | Username: valeriee Mobile number: 92345678 Email: valeriee@hotmail.com Pw: valerie123 (All fields are correct) | Account should be created | N | Form validation said number already used. But when I check against database, number 92345678 has not been used yet. The closest is 92345676 | 2018-06-26
Registration and authentication | 6.2 | Regi 6.2 | Validity of fields other than password | Fill in all fields correctly | Username: jecky Mobile number: 87284869 Email: jecky@hotmail.com Pw: jecky123 (All fields are correct) | Account should be created | N | Form validation said number already used. But when I check against database, number 87284869 has not been used yet.
Registration | 7 | Regi 7 | Validity of password created | Password should contain at least 8 characters | Password is shorter than 8 characters | Password rejected | Y | Logic is correct, accounts cannot be created with passwords shorter However, noted that our configured admin's passwords (eg. prisng's pw ng123) is shorter than 8 characters. For now, for development and testing purposes it is okay, but to change password to a longer one at end of project. | No bugs till date
Registration and authentication | 7.1 | Regi 7.1 | Validity of password created | Password should contain at least 8 characters | Username: jack Mobile number: 81020304 Email: jack@hotmail.com Pw: jack123 (password too short) | Password rejected | Y |  | 2018-06-02
Registration | 8 | Regi 8 | Validity of password created | Password should contain at least 8 characters | Password contains at least 8 characters | Password accepted | N | Couldn't test the intention behind this test type (password creation validity), as the following test cases were failing due to "number already used" even though the numbers entered were new. | 26/6/2018 bug found
Registration and authentication | 8.1 | Regi 8.1 | Validity of password created | Password should contain at least 8 characters | Username: jack Mobile number: 81020304 Email: jack@hotmail.com Pw: jack1234 (password is of correct length) | Password accepted | N | Form validation said number already used. But when I check against database, number 81020304 has not been used yet. It could be that in test case 8.1, even though the account was not created and nothing created in the database's customer table, it is still storing 81020304? Not sure because other numbers which are totally never used before, are flagged up as "number has already been used". | 26/6/2018 bug found
Registration and authentication | 8.2 | Regi 8.2 | Validity of password created | Password should contain at least 8 characters | Username: alex Mobile number: 85858585 Email: alex@hotmail.com Pw: alex1234 (password is of correct length) | Password accepted | N | Form validation said number already used. But when I check against database, number 85858585 has not been used yet. | 26/6/2018 bug found
Registration and authentication | 8.3 | Regi 8.3 | Validity of password created | Password should contain at least 8 characters | Username: alex Mobile number: 81838587 Email: alex@hotmail.com Pw: alex1234 (password is of correct length) | Password accepted | N | Form validation said number already used. But when I check against database, number 81838587 has not been used yet. | 26/6/2018 bug found
Registration | 9 | Regi 9 | Validity of password created | Password should contain at least 8 characters | Password contains at least 8 characters | Password accepted | Y | NIL as no bug | No bugs till date
Registration | 10 | Regi 10 | Validity of password created | Password should contain at least 1 alphabet, 1 number, and 1 special character | Password contains alphabet, no number, no special character | Password rejected | N | Couldn't test the intention behind this test type (password creation validity), as the test cases were failing due to "number already used" even though the number is new. | 2/6/2018 test failed 26/6/2018 cannot test
Registration | 11 | Regi 11 | Validity of password created | Password should contain at least 1 alphabet, 1 number, and 1 special character | Password contains alphabet, number, no special character | Password rejected | N | Couldn't test the intention behind this test type (password creation validity), as the test cases were failing due to "number already used" even though the number is new. | 2/6/2018 test failed 26/6/2018 cannot test
Registration | 12 | Regi 12 | Validity of password created | Password should contain at least 1 alphabet, 1 number, and 1 special character | Password contains no alphabet, have number, no special character | Password rejected | N | Couldn't test the intention behind this test type (password creation validity), as the test cases were failing due to "number already used" even though the number is new. | 2/6/2018 test failed 26/6/2018 cannot test
Registration | 13 | Regi 13 | Validity of password created | Password should contain at least 1 alphabet, 1 number, and 1 special character | Password contains no alphabet, no number, have special character | Password rejected | N | Couldn't test the intention behind this test type (password creation validity), as the test cases were failing due to "number already used" even though the number is new. | 2/6/2018 test failed 26/6/2018 cannot test
Registration | 14 | Regi 14 | Validity of password created | Password should contain at least 1 alphabet, 1 number, and 1 special character | Password contains alphabet, number, special character | Password accepted | N | Couldn't test the intention behind this test type (password creation validity), as the test cases were failing due to "number already used" even though the number is new. | 2/6/2018 test failed 26/6/2018 cannot test
Authentication | 15 | Auth 15 | Validity of password entered (created already, now authenticating) | Password does not match correct password | Different password from correct password | Password rejected | Y | NIL as no bug | No bugs till date
Authentication | 16 | Auth 16 | Validity of password entered (created already, now authenticating) | Password matches correct password. User id and pw to run as follows. Test for both staff and customer accounts. | Password same as correct password | Password accepted | Y | NIL as no bug | No bugs till date
Registration and authentication | 16.1 | Regi 16.1 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: jacky@hotmail.com Pw: jacky | Password accepted | Y
Registration and authentication | 16.2 | Regi 16.2 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: alexia@hotmail.com Pw: alexia | Password accepted | Y
Registration and authentication | 16.3 | Regi 16.3 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: valerie@hotmail.com Pw: valerie | Password accepted | Y
Registration and authentication | 16.4 | Regi 16.4 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: timonthy@hotmail.com Pw: timonthy | Password accepted | Y
Registration and authentication | 16.5 | Regi 16.5 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: audreytan Pw: tan123 | Password accepted | Y
Registration and authentication | 16.6 | Regi 16.6 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: nicolelee Pw: lee123 | Password accepted | Y
Registration and authentication | 16.7 | Regi 16.7 | Validity of password entered (created already, now authenticating) | Password same as correct password | Username: prisng Pw: ng123 | Password accepted | Y
Registration and authentication | 17 | Regi 17 | Security of password storage | Password should be hashed and not stored as plain-text in database | Access database and check if passwords are stored as plain-text | Passwords should not be stored as plain-text | Y | NIL as no bug | No bugs till date
Apptment Booking | 1 | Appt 1 | Check ability to book appointment | Fill in all fields correctly | Fill in all fields correctly | Should be able to book | Y for logic, N for UI | Logic correct, able to book, but some important UI improvements explained below in specific test cases. | 2/6/2018 this UI improvement pt was found 26/6/2018 UI improvement pt remains
Apptment Booking | 1.1 | Appt 1.1 | Check ability to book appointment | Fill in all fields correctly | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: 10/07/2018 Appointment Time: 14:00 (All fields are correct) | Should be able to book | Y | Logic correct, able to book as reflected in database, but it showed a blank page, to show some words like "successful booking" as a pop up instead of only showing at the drop down menu.
Apptment Booking | 1.2 | Appt 1.2 | Check ability to book appointment | Fill in all fields correctly | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: 01/08/2018 Appointment Time: 3pm (All fields are correct) | Should be able to book | N due to UI | Not able to book as I typed "3pm" instead of 15:00. It would be good to have drop-down list or calendar function, instead of free-text.
Apptment Booking | 1.3 | Appt 1.3 | Check ability to book appointment | Fill in all fields correctly | Customer: jacky@hotmail.com Staff: Pris Ng Outlet: Monsoon@Novena Square Treatment: Washing+Drying Appointment Date: 15/08/2018 Appointment Time: 12:30 (All fields are correct) | Should be able to book | Y | Logic correct, able to book as reflected in database, but it showed a blank page, to show some words like "successful booking" as a pop up instead of only showing at the drop down menu.
Apptment Booking | 1.4 | Appt 1.4 | Check ability to book appointment | Fill in all fields correctly | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Bukit Timah Treatment: Washing+Drying Appointment Date: 16/09/2018 Appointment Time: 16.30 (All fields are correct) | Should be able to book | N due to UI | Not able to book as I typed "16.30" instead of 16:30. It would be good to have drop-down list or calendar function, instead of free-text.
Apptment Booking | 2 | Appt 2 | Check ability to book appointment | Fill in fields only partially | Fill in fields only partially | Should not be able to book | Y for logic, N for UI | Logic correct, not able to book as reflected by no booking in database, but the following test cases showed a blank page, to show some words like "unsuccessful booking" instead | 2/6/2018 this UI improvement pt was found 26/6/2018 UI improvement pt remains
Apptment Booking | 2.1 | Appt 2.1 | Check ability to book appointment | Fill in fields only partially | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: left blank Appointment Time: left blank | Should not be able to book | Y
Apptment Booking | 2.2 | Appt 2.2 | Check ability to book appointment | Fill in fields only partially | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: left blank Appointment Time: 14:30 | Should not be able to book | Y
Apptment Booking | 2.3 | Appt 2.3 | Check ability to book appointment | Fill in fields only partially | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: 28/06/2018 Appointment Time: left blank | Should not be able to book | Y
Apptment Booking | 3 | Appt 3 | Check ability to book appointment | Book appointment of the same slot after appointment cancelled | Book appointment of the same slot after appointment cancelled | Should be able to book | Y for logic, N for UI | Logic correct, able to book, but same UI improvement points as test case ID appt 1.1 | 2/6/2018 this UI improvement pt was found 26/6/2018 UI improvement pt remains
Apptment Booking | 3.1 | Appt 3.1 | Check ability to book appointment | Book appointment of the same slot after appointment cancelled | Perform test case 7.1 cancel appointment first. Book again using same parameters, Customer: jacky@hotmail.com Staff: Pris Ng Outlet: Monsoon@Novena Square Treatment: Washing+Drying Appointment Date: 15/08/2018 Appointment Time: 12:30 | Should be able to book | Y
Apptment Booking | 4 | Appt 4 | Check ability to book appointment | Attempt to book appointment before/after opening hours | Attempt to book appointment before/after opening hours | Should not be able to book | Y for logic, N for UI | Logic correct, not able to book as reflected by no booking in database, but the following test cases had me on the same booking page with no info on whether it was booked or not, to show some words like "unsuccessful booking". It would be even better to have drop-down list or calendar function, instead of free-text so this can be validated during input already. | 2/6/2018 this UI improvement pt was found 26/6/2018 UI improvement pt remains
Apptment Booking | 4.1 | Appt 4.1 | Check ability to book appointment | Attempt to book appointment before/after opening hours | Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: 29/06/2018 Appointment Time: 02:00 (2am is before opening hour) | Should not be able to book | Y
Apptment Booking | 4.2 | Appt 4.2 | Check ability to book appointment | Attempt to book appointment before/after opening hours | Customer: jacky@hotmail.com Staff: Pris Ng Outlet: Monsoon@Novena Square Treatment: Washing+Drying Appointment Date: 01/07/2018 Appointment Time: 03:30 (3 30am is before opening hour) | Should not be able to book | Y
Apptment Booking | 5 | Appt 5 | Check ability to book appointment | Attempt to book a 3hour long treatment 1 hour before closing time | Attempt to book a 3hour long treatment 1 hour before closing time | Should not be able to book | TBC | Pending knowledge from client abt how long each service takes at minimum | 2/6/2018 this was TBC 26/6/2018 TBC pending client remains
Apptment Booking | 6 | Appt 6 | Check for conflicts in bookings | Fill in appointment 1 for 1 slot and appointment 2 for the same slot (outlet, time, and stylist) | Fill in appointment 1 for 1 slot and appointment 2 for the same slot (outlet, time, and stylist) | Should not be able to book conflicting appointment. Conflicting appointment is the one who booked later. | N | Validation only worked where it was the same customer booking an appointment he/she already booked. When another customer booked the exact same stylist, outlet, date and time, was wrongly able to book. Should not be able to book. | 26/6/2018 this bug was found
Apptment Booking | 6.1 | Appt 6.1 | Check for conflicts in bookings | Fill in appointment 1 for 1 slot and appointment 2 for the same slot (outlet, time, and stylist) | With reference to test case ID appt 1.1, try to book using same parameters Customer: jacky@hotmail.com Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: 10/07/2018 Appointment Time: 14:00 (All fields are correct) | Should not be able to book conflicting appointment. Conflicting appointment is the one who booked later. | Y | Logic correct, not able to book as reflected by no booking in database, but the following test cases had me on the same booking page with no info on whether it was booked or not, to show some words like "unsuccessful booking". It would be even better to show a calendar view where only available slots are shown
Apptment Booking | 6.2 | Appt 6.2 | Check for conflicts in bookings | Fill in appointment 1 for 1 slot and appointment 2 for the same slot (outlet, time, and stylist) | With reference to test case ID appt 1.1, try to book using same parameters as another customer Log in as Alexia and attempt to book an appointment which Jacky has already booked Staff: Audrey Tan Outlet: Monsoon@Novena Square Treatment: Cutting Appointment Date: 10/07/2018 Appointment Time: 14:00 (All fields are correct) | Should not be able to book conflicting appointment. Conflicting appointment is the one who booked later. | N | Logic incorrect, Alexia was wrongly able to book an appointment Jacky had already booked.
Apptment Booking | 7 | Appt 7 | Check ability to cancel appointment | Cancel appointment made | Cancel appointment made | Should be able to cancel | Y for logic, N for UI | Logic correct, was able to cancel appointment as reflected in deletion of record in database's appointment table, but some UI improvements can be made. Like have a popup to show "Appointment cancelled". Currently these words are at the dropdown menu. | 2/6/2018 this UI improvement pt was found 26/6/2018 UI improvement pt remains
Apptment Booking | 7.1 | Appt 7.1 | Check ability to cancel appointment | Cancel appointment made | With reference to appointment booking test case 1.3, Customer: jacky@hotmail.com Staff: Pris Ng Outlet: Monsoon@Novena Square Treatment: Washing+Drying Appointment Date: 15/08/2018 Appointment Time: 12:30 Attempt to cancel this appointment | Should be able to cancel | Y
Apptment Booking | 8 | Appt 8 | Check ability to guard against spam appointments | From the same IP address, attempt to book 3 appointments within 5min | From the same IP address, attempt to book 3 appointments within 5min | Should not be able to spam bookings from the same IP address | N | To include some validation | 2/6/2018 this bug was found 26/6/2018 bug remains
Apptment Booking | 9 | Appt 9 | Check ability to view appointment | View appointment | View appointment | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y | NIL as no bug | No bugs till date
Apptment Booking | 9.1 | Appt 9.1 | Check ability to view appointment | View appointment | Log in as Jacky and view appointments. | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y
Apptment Booking | 9.2 | Appt 9.2 | Check ability to view appointment | View appointment | Log in as Alexia and view appointments. | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y
Apptment Booking | 9.3 | Appt 9.3 | Check ability to view appointment | View appointment | Log in as Valerie and view appointments. | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y
Apptment Booking | 9.4 | Appt 9.4 | Check ability to view appointment | View appointment | Log in as Timonthee and view appointments. | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y
Apptment Booking | 9.5 | Appt 9.5 | Check ability to view appointment | View appointment | Log in as audreytan and view appointments. | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y
Apptment Booking | 9.6 | Appt 9.6 | Check ability to view appointment | View appointment | Log in as prisng and view appointments. | All appointments made should be listed there. Appointments should tally with database records, which in turn should tally with past appointment booking-related test cases | Y
Member Management | 1 | Memb 1 | Ability to edit user profile | Change display pic | Change display pic | Should be able to change display pic | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed 26/6/2018 cannot test
Member Management | 2 | Memb 2 | Ability to edit user profile | Change mobile number to another valid number | Fill in all 8 digits with numbers, which are not already recorded in the database | Should be able to change mobile number | N | Refer to screenshot on screenshot tab | 26/6/2018 cannot test
Member Management | 3 | Memb 3 | Ability to edit user profile | Attempt to change mobile number to an invalid number | Fill in all 8 digits with numbers which are already existing in the database (duplicate mobile number) | Should not be able to change mobile number | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed 26/6/2018 cannot test
Member Management | 4 | Memb 4 | Ability to edit user profile | Attempt to change mobile number to an invalid number | Do not fill in all 8 digits (eg. fill in 7 digits of phone number) | Should not be able to change mobile number | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed 26/6/2018 cannot test
Member Management | 5 | Memb 5 | Ability to edit user profile | Attempt to change mobile number to an invalid number | Fill in some blanks with alphabets and special characters instead of numbers | Should not be able to change mobile number | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed 26/6/2018 cannot test
Member Management | 6 | Memb 6 | Ability to edit user profile | Change password | See tests in registration and authentication
Member Management | 7 | Memb 7 | Ability to edit user profile | Change email | Fill in new email address which is not already recorded in the database | Should be able to change email address | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed as no such functionality 26/6/2018 cannot test
Member Management | 8 | Memb 8 | Ability to edit user profile | Attempt to change email address to a duplicate email address | Fill in new email address, which is already existing in the database | Should not be able to change email address | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed as no such functionality 26/6/2018 cannot test
Member Management | 9 | Memb 9 | Ability to view loyalty points history | View loyalty points history | View loyalty points history | Should be able to view loyalty points history | N | Refer to screenshot on screenshot tab | 2/6/2018 test failed 26/6/2018 cannot test
Member Management | 10 | Memb 10 | Ability to view loyalty points history | Attempt to edit loyalty points history | Attempt to find a button to edit loyalty points | Should have no such edit button | N | Can't test as can't view loyalty points history | 26/6/2018 cannot test
Member Management | 11 | Memb 11 | Ability to view treatment history | View treatment history | View treatment history | Should be able to view treatment history | Y | Refer to screenshot on screenshot tab | 26/6/2018 this bug was found
Member Management | 12 | Memb 12 | Ability to view treatment history | Attempt to edit treatment history | Attempt to find a button to edit treatment history | Should not be able to edit treatment history | N | Can't test as can't view treatment history | 26/6/2018 cannot test
UT | 1 | UT 1 | User Testing findings | User Testing findings | Blank screen met after making bookings. Same as encountered in internal testing. Refer to test ID 1.1 for example of parameters used internally when encountered this same bug | Confirmation screen should be shown | N due to UI |  | Refer to test ID appt booking 1.1 for history
UT | 2 | UT 2 | User Testing findings | User Testing findings | Navigation bar, links are not working | Navigation bar links should be working | N |  | 28/6/2018 this bug was found
UT | 3 | UT 3 | User Testing findings | User Testing findings | [UI improvement] For creating new user account. User was not alerted to his incorrect typing of pw in the confirm pw field. Username: Marvin Mobile number: (Put in any valid number) Email: (Put in any valid email) Pw: (Put in any password) Confirm Pw: (Put in a different pw from the earlier field) | Validation alert to show wrong pw entered in the confirm pw field should be shown | N due to UI |  | 28/6/2018 this UI improvement pt was found
UT | 4 | UT 4 | User Testing findings | User Testing findings | [UI improvement] To improve table layout in various functions, eg. inventory function view inventory, table layout should be moved to calendar layout for appointment booking related | No fixed "correct outcome", but to improve UI from existing table layout | N due to UI |  | 28/6/2018 this UI improvement pt was found
UT | 5 | UT 5 | User Testing findings | User Testing findings | [UI Improvement] For add new inventory form, remove comment field as user was questioning the point of having this field. | Fields in the add new inventory form (or any form for that matter), should have a purpose | N due to UI
UT | 6 | UT 6 | User Testing findings | User Testing findings | Completed bookings function not working. User marked some appointments as completed, but he was met with a blank page instead. Did not test this function internally, so do not know if it went to the database but just the UI side not working, or it did not even go to the database. | Bookings marked as completed, should show in the completed bookings function | N |  | 28/6/2018 this bug was found
UT | 7 | UT 7 | User Testing findings | User Testing findings | [UI Improvement] In making new appointment booking, I noticed that even though the time correctly validates for opening/closing hours, those hours should not even be on the dropdown time list. Eg. 10:00 is in the drop-down list, but opening hour is only 11:00 so doesn't make sense to have it on the list and allow user to select it, only to tell them it is before/after operating hours | Do not have hours which are before/after operating hours, to be shown on the drop-down list | N due to UI |  | 28/6/2018 this UI improvement pt was found
UT | 8 | UT 8 | User Testing findings | User Testing findings | [UI Improvement] Change password cannot be found on drop-down menu. Change password was at the login page, underneath the login fields, which should have been Forget password instead. | Move change password to drop-down menu after user logs in. Change the change password link at the login page, to a forget password function | N due to UI |  | 28/6/2018 this UI improvement pt was found
Note on H1: Legend for bugs found and corresponding severity Blue Minor because it relates to a security feature or will be fixed when UI is up Yellow Moderate because it affects functionality
Note on H10: Note: Even though there are multiple yellow highlights (i.e. moderate severity), do not be alarmed. They pertain to the same bug, the "number already used" validation even though numbers entered were new.

## Screenshot
Screenshot for Test Case ID Memb 1, 2, 3, 4, 5, 7, 8:
Screenshot for Test Case ID Memb 9, 11: